## Sheet1
Burn down chart TKPPL Bespoke Dubasata
Project | Story | Task | Task | Start | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Presentasi Dubasata | Definisi Virtual Reality |  | Menjelaskan Definisi VR | 4 | 2 | 0 | 0
Presentasi Dubasata | Sejarah Virtual Reality |  | Menjelaskan Sejarah VR | 4 | 0 | 0 | 0
Presentasi Dubasata | Cara kerja Virtual Reality |  | Menjelaskan Cara Kerja VR | 7 | 7 | 7 | 5
Presentasi Dubasata | Element Virtual Reality |  | Menjelaskan Element VR | 6 | 6 | 6 | 0
Presentasi Dubasata | Alat-alat Virtual Reality |  | Menjelaskan Alat-alat pendukung VR | 4 | 4 | 4 | 2
Presentasi Dubasata | Software Virtual Reality |  | Mejelaskan Software yang dibutuhkan VR | 3 | 3 | 3 | 3
Presentasi Dubasata | Kelebihan Utama Virtual Reality |  | Menjelaskan Kelebihan VR | 5 | 5 | 5 | 5
Presentasi Dubasata | Efek Negatif Virtual Reality |  | Menjelaskan Kekurangan VR | 5 | 5 | 5 | 5
Presentasi Dubasata | Penerapan Virtual Reality |  | Menjelaskan Penerapan dikehidupan sehari-hari | 8 | 8 | 8 | 8
Presentasi Dubasata | Virtual Reality Di Masa Depan |  | Menjelaskan Perkembangan VR di masa depan | 8 | 8 | 8 | 8
Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 54 | 48.6 | 43.2 | 37.8
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 54 | 48 | 46 | 36
Note on G6: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered