## Sheet1
Burn down chart TKPPL Bespoke Dubasata
Project | Story | Task | Task | Start | Day 13 | Day 12 | Day 11 | Day 10 | Day 9 | Day 8 | Day 7 | Day 6 | Day 5 | Day 4 | Day 3 | Day 2 | Day 1
Presentasi Dubasata | Definisi Virtual Reality |  | Menjelaskan Definisi VR | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Sejarah Virtual Reality |  | Menjelaskan Sejarah VR | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Cara kerja Virtual Reality |  | Menjelaskan Cara Kerja VR | 7 | 7 | 7 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Element Virtual Reality |  | Menjelaskan Element VR | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Alat-alat Virtual Reality |  | Menjelaskan Alat-alat pendukung VR | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Software Virtual Reality |  | Mejelaskan Software yang dibutuhkan VR | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Kelebihan Utama Virtual Reality |  | Menjelaskan Kelebihan VR | 5 | 5 | 5 | 5 | 4 | 4 | 4 | 4 | 4 | 0 | 0 | 0 | 0 | 0
Presentasi Dubasata | Efek Negatif Virtual Reality |  | Menjelaskan Efek Negative VR | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 3 | 3 | 3 | 2 | 1 | 1 | 0
Presentasi Dubasata | Penerapan Virtual Reality |  | Menjelaskan Penerapan dikehidupan sehari-hari | 8 | 8 | 8 | 8 | 8 | 8 | 6 | 5 | 5 | 5 | 5 | 4 | 4 | 0
Presentasi Dubasata | Virtual Reality Di Masa Depan |  | Menjelaskan Perkembangan VR di masa depan | 8 | 8 | 8 | 8 | 8 | 8 | 7 | 6 | 6 | 5 | 5 | 3 | 3 | 0
Ideal - Remaining efforts in uninterrupted working hours |  |  |  | 54 | 49.8462 | 45.6923 | 41.5385 | 37.3846 | 33.2308 | 29.0769 | 24.9231 | 20.7692 | 16.6154 | 12.4615 | 8.3077 | 4.1538 | 0
Actual - Remaining efforts in uninterrupted working hours |  |  |  | 54 | 48 | 46 | 34 | 33 | 28 | 25 | 21 | 21 | 13 | 12 | 8 | 8 | 0
Note on G6: goodoldmanoj.com: Remaining effort as of that day to complete the task. NOT last day effort - hours worked. So this can go up if new challenges got uncovered